## Cover Sheet
Organization Impact Assessment Matrix
Version: 0.1
Author(s): | Michelle King
Phase:
Approver(s):
Submitted:
Reviewed:
Date | Version | Description | Author(s)

## Adoption
# |  |  | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Current | New |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[7 empty] | C | T | PS | JD | O
1 |  |  | Piedmont provides no adoption coverage for non-unionized employees | Provides $5K expense coverage for adoption of children including step children or those that meet definition of dependent under IRS | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs/ Heads up to managers | Bundled communication - new benefit (positive for employees)/ Heads up communication to HRBPs/managers of Piedmont employees; HRBP Training
1a |  |  | Piedmont provides no adoption coverage for unionized employees | Provides $5K expense coverage for adoption of children including step children or those that meet definition of dependent under IRS | L | Skill/Knowledge | C | T |  |  |  | Unionized employees - IBEW 1902 / PPF | Communication separately to unionized employees
2 |  |  | No forms or process in place | Duke Energy's adoption administrator to answer questions and help with forms | L | Volume | C |  |  |  |  | Kit Rose | Provide updates to Kit
3 |  |  | N/A | Opportunity to process in Workday to use one-time payment | L | Skill/Knowledge | C | T |  |  |  | Duke Managers | Included in employee bundled communication ('read package'), but highlight new process (Duke managers to submit and upload form in Workday) / HRBPs / Managers receive training during Roadshows in November

## EAP
# |  |  | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Current | New |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[7 empty] | C | T | PS | JD | O
1 |  |  | Current vendor to change - EAP is McLaughlin Group | Change to Duke Energy vendor - Optium Health | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs/ Heads up to managers | Bundled communication - new vendor / process; HRBP Training
2 |  |  | Program:*One where the manager suspects an issue based on employee habits of tardiness, agitation toward other employees, smell of alcohol but not confirmed by another manager. The manager notifies ER and provides the brochure and suggests the employee contact EAP * Second where the manager is sure of threats to employees, is sure of a substance abuse issue or other action that might put the employee or co-workers in danger. The manager notifies the assigned HR Business Consultant and a call is made by HR or with the manager to EAP. The employee is out of work until EAP advises that the employee completed the treatment plan satisfactorily and notifies HR Business Consultant that the person is able to return to work or recommends additional treatment/next steps. | Management Referral Program - 'Fit for duty' | M | Skill/Knowledge | C | T |  |  |  | HRBPs and managers to understand the process / Employees in current Piedmont program | Transition program for open current management referrals? - TBD

## Education Assistance
# |  |  | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Current Piedmont | New |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[7 empty] | C | T | PS | JD | O
1 |  |  | Piedmont max is $10,000 | Duke offers max of $5,250 reimbursement per year | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs/ Heads up to managers
2 |  |  | Piedmont lifetime max of $40,000 | Duke offers no lifetime maximum | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs/ Heads up to managers
3 |  |  | Reimbursement process through Workday | Expense Management System - new code - TBD | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs/Education Administrator (Kit Rose) | Jennifer Edwards / Kamille discussing (will not be in Workday)
4 |  |  | N/A | 1. Select the Duke Energy policy a. Piedmont employees will start Jan. 1, 2018 with the new policy of an annual maximum of $5,250 per year 2. Remain in the legacy Piedmont lifetime maximum of $40,000 a. This option provides an annual maximum of $10,000 b. Legacy Piedmont employees will follow the legacy Duke Energy reimbursement process c. This option will expire Jan. 1, 2020 |  | Responsibilities | [5 empty] | Piedmont Employees participating in Continuing Education Program / Heads up to Managers of those employees | Nov communication
Piedmont Employees Currently Participating in the program: | [12 empty] | Retire Program; Adopt DE Program (less rules; less benefits annually, but no lifetime max.
1 |  |  | Piedmont Natural Gas (Piedmont) supports employee participation in educational opportunities to further current role development or enhance capabilities for movement within the Company. Piedmont provides educational assistance to eligible employees pursuing approved academic coursework and degree programs at accredited educational institutions | Duke Energy promotes the continuing educational and professional development of employees by reimbursing employees for the costs of certain educational courses, programs, and exams as described below | L |  | C |  |  |  |  | Piedmont Employees currently in program | To be grandfathered into current program
2 |  |  | To apply for participation in Piedmont’s Education Assistance Program for an associate or undergraduate degree, an employee must meet each of the following eligibility requirements: a) have six months of continuous service with the Company at the time of the request (See HR Policy #2007 Introductory Period) b) be actively at work in a full time, part time or seasonal position  Note: Temporary employees and part time employees regularly scheduled for 19 or fewer hours per week are not eligible for participation. c) have satisfactory performance in their current job i. satisfactory or better on most recent individual MVP performance plan ii. no active Performance Improvement Plan (PIP) iii. no more than one active disciplinary action and none above the level of first written warning | Eligibility Employees are eligible to participate in the Education Assistance Program if they are: • Regular full-time, fixed term or part-time employees who are actively employed by Duke Energy at the time of enrollment • On an approved leave of absence and are already participating in the Education Assistance Program and attending classes for the current term begun prior to the initiation of the leave. Otherwise, employees on a leave of absence will need to return to work before initiating participation in the Education Assistance Program.
3 |  |  | To apply for participation in Piedmont’s Education Assistance Program for a graduate degree, an employee must meet the basic eligibility requirements listed above and the following additional requirements: a) hold a supervisory or management position or a comparable professional level position, and b) must have shown leadership in a Piedmont sponsored program such as the Compass Program, serving as a PNGU facilitator (or facilitating other Piedmont training), or chairing a Piedmont-sponsored committee such as United Way, Arts & Science, Heartwalk, etc. and tenure with Piedmont that demonstrates sustained high level of performance (minimum of three to five years)All degree course work must be completed at an academic degree granting institution with accreditation in good standing recognized by the US Department of Education. In addition, the coursework must qualify for transferable college credits. | Approval Requirements Although not required, it is recommended that employees discuss their educational plans with management prior to beginning a course of study for career planning purposes. However, prior approval of supervision is required if course schedules are not compatible with work schedules or might interfere with the employee’s availability for work. Approved institutions are only those listed in the Accredited Institutions of Postsecondary Education published annually by the American Council on Education, which lists all colleges, universities, and other postsecondary educational institutions in the United States and elsewhere that are accredited by organizations recognized by the Council for Higher Education Accreditation or the U.S. Department of Education.
4 |  |  | To apply for the Education Assistance Program, an employee must: a) fully complete Piedmont’s Degree Program Application, which includes a paragraph (“Employee Statement”) stating the reasons for pursuing a degree and career goals, and obtain written recommendation from the employee’s supervisor b) provide a copy of degree curriculum requirements c) provide a copy of the educational institution’s accreditation, and d) complete application process in Workday (job aid available) When considering the request, supervisors should consider the employee’s job performance and any conflicts with work responsibilities and scheduled work hours. The total cost of the degree program and any viable options for less expensive programs should also be considered. All applications (including all required information as noted in this section) must be submitted through Workday no less than 30 days in advance of course, degree, or program start dates. All applications will be reviewed and considered for approval based on information submitted by the applicant by the Education Assistance Committee. Additionally, applications for participation in a graduate degree program must include written recommendation from an employee’s manager with justification for purposes of Succession Planning, Affirmative Action or Workforce Planning requirements. | Within 60 days after satisfactory course completion, the employee must complete the reimbursement section of the application and apply for the amount of the reimbursement requested. Supporting documentation (Sections A & B of the application, grade report and itemized tuition/fee bill on institution letterhead and itemized receipts for other qualified expenses) should be submitted with the reimbursement request.
5 |  |  | Final approval for associate and undergraduate degree program participation shall be a Managing – Human Resources or designee. Employees requesting approval for a graduate degree program must undergo an interview with a Managing Director – Human Resources, the Senior Vice President & Chief Administrative Officer, and the Senior Vice President of the employee’s functional area. Final approval for a graduate degree program requires approval by the full Executive Management Team who will consider: the application, the written recommendation by the applicant’s manager, the results of the interview and the Education Assistance budget when making its decision. The applicant will receive notification confirming approval or denial of degree program participation. | Reimbursement limits apply to the year in which reimbursements are actually paid, and not in the year the courses were taken or when the initial expenses were incurred. The Company will reimburse eligible employees up to $5,250 annually for covered educational expenses for undergraduate and graduate studies. This is an annual cap that may not be exceeded, but there is no lifetime maximum.
|  |  | Piedmont will reimburse program participants for the actual amount of costs associated with tuition and books or texts required for approved coursework. Effective with reimbursements made after July 1, 2012, Piedmont will reimburse to a maximum of $10,000 per calendar year and $40,000 lifetime maximum for each employee. Reimbursement is not provided for any other expenses, including but not limited to fees (activity, deferral, graduation, technology/ lab), parking, purchase or lease of personal computers, software, or other equipment or supplies that may be suggested or required for successful course completion. Payment pro-rated based on grades: A B or Pass = 100% C = 50%; Part-time employees: A B or Pass 50%. C = 25% | In order to be reimbursed, employees must receive a grade of C or higher or pass the course if it is taken on a Pass/Fail basis. Audited classes are not eligible for reimbursement.
Duke Energy Managers of Piedmont Employees participating in program
|  |  | See current Piedmont | See New Duke | L |  | C |  |  |  |  | Managers/ Supervisors of employees currently in program | Provide heads up communication and talking points, as needed
All Piedmont Employees
|  |  | See current Piedmont | See New Duke | L |  | C |  |  |  |  | Piedmont Employees | Communicate new policy guidelines
Duke Energy Managers of Piedmont Employees
|  |  | See current Piedmont | See New Duke | L |  | C |  |  |  |  | Managers/ Supervisors | Provide heads up communication and talking points, as needed

## Overlapping Initiatives (hidden)
# |  |  | Overlapping Initiatives |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Project / Description | Current Status |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support JD - Job Design / Org Design O - Other
[7 empty] | C | T | PS | JD | O
Overlapping Initiatives
1 |  |  | Legal Entity Management: Scope includes enterprise-wide strategy, guidance, and accountability for legal entity management. Contact: Mike Brenden | Legal Entities codes are determined by the time used in COA/code block. SA Vince Castellese meets bi-weekly with LE Team. | L | N/A |  |  |  |  | x | All GMAC | Each initiative will provide its own transition management activities. Autobahn's transition management team is not responsible for any communications and/or training for any of the overlapping initiatives.
2 |  |  | Finance Shared Services (FSS): Scope include Transaction Processing activities including Payables, Fixed Assets, and General Ledger activities based on current systems. Contact: Alex Gonzalez | WNS partner may use SAP-related transactions. FSS Transition Management will provide transition management activities if necessary. | M | N/A |  |  |  |  | x | Finance Organization | See above
3 |  |  | FS-CD (SAP Collections and Disbursement) for Insurance. Scope is to replace the current legacy systems used at MIC, UWC and Car Care Plan to provide harmonized billing, collections and disbursements functions with SAP FS-CD application. Contact: John Baio | Roll-out planned for Q2 2009 for UWC and MIC for 2010. No Autobahn transition management activities will be provided. Vince meets w/team bi-weekly. | L | N/A |  |  |  |  | x | Insurance | See above
4 |  |  | Purchasing Application (ARIBA): Scope include for all business units including the invoice matching and approval and management. Contacts: Joyce Korfeld, Jim McQuide | Roll-out at ResCap planned for September. No Autobahn transition management activities will be provided. - If ARIBA does not get implemented then the overall scope for PO will need to be addressed by Autobahn. - Timing for implementation of PO w/in Autobahn will be lagging behind given where we are with everything else. | M/H | N/A |  |  |  |  | x | GMAC | ARIBA implementation is still under discussion.
5 |  |  | MRS: Management Reporting Strategy (Finance): Scope is to determine common reporting dimensions and definitions across the Finance Organization. Contact: Anne Beck | Project has delayed the development of their report list and functional specs until after key strategy decision are made relating to EDW and enterprise reporting tool strategies are completed. No known Transition Management activities at this time. SA Vince Castellese works with team. | L | N/A |  |  |  |  | x | Finance Organization | See above
6 |  |  | EDW-Enterprise Data Warehouse (Enterprise): Scope includes management reporting information including reporting definitions, data structures, and multiple source data initiatives. Contact: Jeff Wiener | Project not active at this time. | L | N/A |  |  |  |  | x | GMAC | See above
7 |  |  | Global Travel and Expense (Concur): Scope includes travel and expense tracking and reporting processes across all business units. Contact: Lisa Starr | No Autobahn transition management activities. | L | N/A |  |  |  |  | x | All GMAC | See above
8 |  |  | Transaction System Upgrades: Scope includes improving transaction systems to support daily posting of the general ledger across GMAC. Contact: Jeff Weiner | No Autobahn transition management activities. | L | N/A |  |  |  |  | x |  | See above
9 |  |  | OneHR: Harmonization of GMAC HR processes, including Payroll, metadata, etc. and PS platform. Deploy GMAC-wide LMS for learning. Contact: Jeff Joachim | No Autobahn transition management activities. | M | Skill-Knowledge- Plan to deliver Autobahn training via LMS |  |  |  |  | x | All GMAC | See above
European Initiatives: will contact Oliver Kipping for info on possible initiatives.

## FAC - Other Impacts (hidden)
| Financial Accounting |  |  |  | Options: High, Medium, Low
| External Financial Reporting | Barbara (NAO Controllers)
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Low | Low | Low
2 | Training and Communications | Medium | Low | Low / Medium
3 | Systems and Tools | Medium | Low | Medium | There are some interfaces that may be required to SAP GL to gain additional detail.
4 | Potential Barriers | Low | Low | Low
| Maintain Financial Master Data | Kevin Warner or Evelina (EMEA)
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Medium / High | Medium | Medium | There is the need to streamline master data across FAC MAC TRP. COE/FSS groups will be impacted with the to-be process design.
2 | Training and Communications | Low | Low | Low
3 | Systems and Tools | Medium | Low | Medium
4 | Potential Barriers | Low | Low | Low
| Process Intercompany Transactions | Tim & Jay (IO)
| Impact Category | Depth | Breadth | Overall | Comments | Notes
1 | Workforce (Organization, Leadership, People) | High | High | High | There are some countries that do not allow posting from non-residents thus cross border intercompany is under review. | There are some countries that cannot book to their GL.
2 | Training and Communications | Medium | Medium | Medium | Training will be key RE: proper code blocking. Job aids and FAQ may be required. - Focused communications may be required for specific groups that want to begin enforcing this process prior to deployment. (i.e. insurance, potentially NAO). Dependency: GC decision post workshop | Eliminate the # of entries to "have to" review. There is a need for reviews but they do not have to be from a mgr level person necessarily.
3 | Systems and Tools | Low | Low | Low | Medium for those than do not have SAP today.
4 | Potential Barriers | Medium | Medium | Medium | - Culture is the biggest barrier. People don't want others to book w/in their books. - Local regulations and complexity for Taxes (i.e. VAT)
| Process Journal Entries | Tim
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | High | High
2 | Training and Communications | Low / Medium | Low / Medium | Low / Medium | Park/Post will be the global standard however local deviation will be allowed. None SAP user change/impact will be higher - this makes the overall impact low - medium. | There are multiple SAP codes that people don't know translation to. Opportunity to do a FA Codes as a job aid. Do we need a proper policy for journal entry to advice on park/post, sox, etc.
3 | Systems and Tools | Low | Low | Low |  | Too many excel templates???
4 | Potential Barriers | Medium | Medium | Medium | This may change depending on the final decision for Park/Post.
| Manage Interfaces | Tim
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | Medium | Medium | Volume of interfaces is high but no changes are foreseeable at the moment.
2 | Training and Communications | Low | Low | Low
3 | Systems and Tools | Low | Low | Low
4 | Potential Barriers | Low | Low | Low | We may not be able to provide as much automation as requested w/in the timeframes assigned.
| Analyze and Reconcile Accounts | Christina Higgins (Corporate Consolidations) & Sanjeev
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Medium | Medium | Medium
2 | Training and Communications | Low / Medium | Low / Medium | Low / Medium | Autobahn will deploy SAP standard functionality which will require familiarity with SAP standard reports to perform the reconciliation.
3 | Systems and Tools | Medium | Medium | Medium | Currently all OS doing recon outside of SAP (even if they already have it).
4 | Potential Barriers | Low | Low | Low | Compliance is the main barrier in this case.
| Close Period and Consolidate | Christina Higgins (Corporate Consolidations) & Jay Rogers (IO)
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | High | High | There are no new processes for forecast and planning (OOS). The only exception is Auto Finance - Euro
2 | Training and Communications | High | High | High | Include scenarios of typical issues. Analysis and troubleshooting skills.
3 | Systems and Tools | High | High | High
4 | Potential Barriers | High | High | High | Resistance to change on tools (i.e. Hyperion - used at NAO, ResCap, IO, GMAC Corp)
| Chart of Accounts: Code Block | KW & CH
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | High | High | It is a new mind set for EVERYONE
2 | Training and Communications | High | High | High
3 | Systems and Tools | Low | Low | Low | SAP users do not currently use it to the full extent
4 | Potential Barriers | Medium | Medium | Medium | Gaining acceptance to a global COA.
Note on C4: Refers to the # of Business Units w/in a single Op Segment.
Note on D4: # of Op Segments

## Mgmt Accy - Other Impacts (hidden)
| Mgmt Accounting |  |  |  | Options: High, Medium, Low
| Month End Close | Keith Milenius
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Med/High | High | High | There is a need for agreement on which processes are going to be handled by COE vs. businesses. There are some month end close activities that makes more sense to be done locally, not by COE.
2 | Training and Communications | High | High | High | Training for both COE and BUs
3 | Systems and Tools | High | High | High
4 | Potential Barriers | Low | Low | Low | BU may question responsiveness of COE vs. doing it locally
| Maintain and Control Master Data | Regina White
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Medium / High | Medium | Medium | Includes new allocation methods
2 | Training and Communications | Med | Medium | Medium | Training will be key RE: proper code blocking. Job aids and FAQ may be required. - Communications may be required for specific groups that want to begin enforcing this process prior to deployment. (i.e. insurance, potentially NAO). Dependency: GC decision post workshop results.
3 | Systems and Tools | High | High | High
4 | Potential Barriers | Low | Low | Low
| Management Accounting - COE Processes | Bruce Bissell
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Med/High | High | High | Only Ins and IO Europe familiar with COE
2 | Training and Communications | High | High | High | COE and BU training
3 | Systems and Tools | High | High | High
4 | Potential Barriers | Low | Low | Low
| Management Accounting - Business Processes | Bruce Bissell
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | Med/High | High | High | Only Ins and Europe familiar with COE, will impact BUs planning and monthly forecasting
2 | Training and Communications | High | High | High | COE and BU training
3 | Systems and Tools | High | High | High
4 | Potential Barriers | Low | Low | Low
| Capture, Track Costs Posting Actuals | Srivaths
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | High | High | WBS: for ALL ITG
2 | Training and Communications | High | High | High | WBS: for ALL ITG
3 | Systems and Tools | Low | Low | Low | Ariba, FSS feed info, month and adhoc reporting
4 | Potential Barriers
| Close Projects | Srivaths
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | High | High | WBS: for ALL ITG
2 | Training and Communications | High | High | High | WBS: for ALL ITG
3 | Systems and Tools | Low | Low | Low
4 | Potential Barriers
| Period End Close- Project Systems | Srivaths
| Impact Category | Depth | Breadth | Overall | Comments
1 | Workforce (Organization, Leadership, People) | High | High | High | WBS: for ALL ITG
2 | Training and Communications | High | High | High | WBS: for ALL ITG
3 | Systems and Tools | Low | Low | Low
4 | Potential Barriers
Note on C5: Refers to the # of Business Units w/in a single Op Segment.
Note on D5: # of Op Segments

## Commuter Benefits
# |  |  | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Current | New |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[7 empty] | C | T | PS | JD | O
1 |  |  | No parking benefit | Parking Benefit - All eligible employees can receive a subsidy of up to $60 per month to pay for parking in approved metropolitan areas. | L | Skill/Knowledge | C | T |  |  |  | Heads up to Managers / All Piedmont Employees /HRBPs | November Communications: Commuter Benefits (sign up process by Dec. 8) / Direct employees to Employee Center > Commuter Benefits page (FAQs). Eligibility file to include PNG employees will be 11/20/17; HRBP Training
2 |  |  | No mass transit benefit | Mass Transit Benefit - The mass transit benefit available through the Commuter Benefits Program stipulates that 100 percent of work-related mass transit costs are subsidized by the company. Employees do not have to contribute any funds to receive the mass transit benefit. | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs | To receive the mass transit benefit, employees must incur work-related mass transit costs and establish an account with the Duke Energy Commuter Benefit provider; HRBP Training

## Leave of Absence - Parental
# | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Current | New |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[5 empty] | C | T | PS | JD | O

## Military Leave (part of Leaves)
# |  |  | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Current Piedmont | New | Overall Positive | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[7 empty] | C | T | PS | JD | O
1 |  |  |  | + Annual Training of 80 hours per calendar year at 100% base pay vs. pay coordination for up to 3 weeks + Pay coordination for up to 5 years; refreshes with each deployment – Employee has to pay full cost of benefit coverage after 6 months of pay coordination vs. after 18 months | L |  | C | T |  |  |  | All Piedmond Employees | Bundled communication to Piedmont Employees / HRBP Training
2 |  |  |  | + Annual Training of 80 hours per calendar year at 100% base pay vs. pay coordination for up to 3 weeks + Pay coordination for up to 5 years; refreshes with each deployment – Employee has to pay full cost of benefit coverage after 6 months of pay coordination vs. after 18 months | L |  | C | T |  |  |  | Those currently on Military leave 1/1/18 | Home mailing?
3 |  |  | Military Leave - pay continuation for six months, pay coordination thereafter. 18 month lifetime maximum; Annual Training provided with pay coordination. | Military Leave - Pay continuation for two full pay periods to enable employees to provide military pay stub to LM. Pay coordination for up to 5 years - refreshed with each deployment. 80 hour bank for annual training at 100% pay; refreshed annually. | L |  | C | T |  |  |  | All Piedmont Employees; Targeted communication; HRBP Training | Bundled communication to Piedmont Employees / HRBP Training; Identify who is actively on military leave to do targeted communication how to handle each case (bring them over to Duke policy which will be more beneficial)
Piedmont Employees Currently Participating in the program: | [12 empty] | Retire Program; Adopt DE Program (less rules; less benefits annually, but no lifetime max.
1 |  |  | Piedmont Natural Gas (Piedmont) supports employee participation in educational opportunities to further current role development or enhance capabilities for movement within the Company. Piedmont provides educational assistance to eligible employees pursuing approved academic coursework and degree programs at accredited educational institutions | Duke Energy promotes the continuing educational and professional development of employees by reimbursing employees for the costs of certain educational courses, programs, and exams as described below | L |  | C |  |  |  |  | Piedmont Employees currently in program | To be grandfathered into current program
2 |  |  | To apply for participation in Piedmont’s Education Assistance Program for an associate or undergraduate degree, an employee must meet each of the following eligibility requirements: a) have six months of continuous service with the Company at the time of the request (See HR Policy #2007 Introductory Period) b) be actively at work in a full time, part time or seasonal position  Note: Temporary employees and part time employees regularly scheduled for 19 or fewer hours per week are not eligible for participation. c) have satisfactory performance in their current job i. satisfactory or better on most recent individual MVP performance plan ii. no active Performance Improvement Plan (PIP) iii. no more than one active disciplinary action and none above the level of first written warning | Eligibility Employees are eligible to participate in the Education Assistance Program if they are: • Regular full-time, fixed term or part-time employees who are actively employed by Duke Energy at the time of enrollment • On an approved leave of absence and are already participating in the Education Assistance Program and attending classes for the current term begun prior to the initiation of the leave. Otherwise, employees on a leave of absence will need to return to work before initiating participation in the Education Assistance Program.
3 |  |  | To apply for participation in Piedmont’s Education Assistance Program for a graduate degree, an employee must meet the basic eligibility requirements listed above and the following additional requirements: a) hold a supervisory or management position or a comparable professional level position, and b) must have shown leadership in a Piedmont sponsored program such as the Compass Program, serving as a PNGU facilitator (or facilitating other Piedmont training), or chairing a Piedmont-sponsored committee such as United Way, Arts & Science, Heartwalk, etc. and tenure with Piedmont that demonstrates sustained high level of performance (minimum of three to five years)All degree course work must be completed at an academic degree granting institution with accreditation in good standing recognized by the US Department of Education. In addition, the coursework must qualify for transferable college credits. | Approval Requirements Although not required, it is recommended that employees discuss their educational plans with management prior to beginning a course of study for career planning purposes. However, prior approval of supervision is required if course schedules are not compatible with work schedules or might interfere with the employee’s availability for work. Approved institutions are only those listed in the Accredited Institutions of Postsecondary Education published annually by the American Council on Education, which lists all colleges, universities, and other postsecondary educational institutions in the United States and elsewhere that are accredited by organizations recognized by the Council for Higher Education Accreditation or the U.S. Department of Education.
4 |  |  | To apply for the Education Assistance Program, an employee must: a) fully complete Piedmont’s Degree Program Application, which includes a paragraph (“Employee Statement”) stating the reasons for pursuing a degree and career goals, and obtain written recommendation from the employee’s supervisor b) provide a copy of degree curriculum requirements c) provide a copy of the educational institution’s accreditation, and d) complete application process in Workday (job aid available) When considering the request, supervisors should consider the employee’s job performance and any conflicts with work responsibilities and scheduled work hours. The total cost of the degree program and any viable options for less expensive programs should also be considered. All applications (including all required information as noted in this section) must be submitted through Workday no less than 30 days in advance of course, degree, or program start dates. All applications will be reviewed and considered for approval based on information submitted by the applicant by the Education Assistance Committee. Additionally, applications for participation in a graduate degree program must include written recommendation from an employee’s manager with justification for purposes of Succession Planning, Affirmative Action or Workforce Planning requirements. | Within 60 days after satisfactory course completion, the employee must complete the reimbursement section of the application and apply for the amount of the reimbursement requested. Supporting documentation (Sections A & B of the application, grade report and itemized tuition/fee bill on institution letterhead and itemized receipts for other qualified expenses) should be submitted with the reimbursement request.
5 |  |  | Final approval for associate and undergraduate degree program participation shall be a Managing – Human Resources or designee. Employees requesting approval for a graduate degree program must undergo an interview with a Managing Director – Human Resources, the Senior Vice President & Chief Administrative Officer, and the Senior Vice President of the employee’s functional area. Final approval for a graduate degree program requires approval by the full Executive Management Team who will consider: the application, the written recommendation by the applicant’s manager, the results of the interview and the Education Assistance budget when making its decision. The applicant will receive notification confirming approval or denial of degree program participation. | Reimbursement limits apply to the year in which reimbursements are actually paid, and not in the year the courses were taken or when the initial expenses were incurred. The Company will reimburse eligible employees up to $5,250 annually for covered educational expenses for undergraduate and graduate studies. This is an annual cap that may not be exceeded, but there is no lifetime maximum.
|  |  | Piedmont will reimburse program participants for the actual amount of costs associated with tuition and books or texts required for approved coursework. Effective with reimbursements made after July 1, 2012, Piedmont will reimburse to a maximum of $10,000 per calendar year and $40,000 lifetime maximum for each employee. Reimbursement is not provided for any other expenses, including but not limited to fees (activity, deferral, graduation, technology/ lab), parking, purchase or lease of personal computers, software, or other equipment or supplies that may be suggested or required for successful course completion. Payment pro-rated based on grades: A B or Pass = 100% C = 50%; Part-time employees: A B or Pass 50%. C = 25% | In order to be reimbursed, employees must receive a grade of C or higher or pass the course if it is taken on a Pass/Fail basis. Audited classes are not eligible for reimbursement.
Duke Energy Managers of Piedmont Employees participating in program
|  |  | See current Piedmont | See New Duke | L |  | C |  |  |  |  | Managers/ Supervisors of employees currently in program | Provide heads up communication and talking points, as needed
All Piedmont Employees
|  |  | See current Piedmont | See New Duke | L |  | C |  |  |  |  | Piedmont Employees | Communicate new policy guidelines
Duke Energy Managers of Piedmont Employees
|  |  | See current Piedmont | See New Duke | L |  | C |  |  |  |  | Managers/ Supervisors | Provide heads up communication and talking points, as needed

## Service Awards
# |  |  | Change |  | Impact | Impact Description | Intervention |  |  |  |  | Impacted Groups | Notes
| Process Area | Process Pack | Current | New |  | o Volume o Complexity o Responsibilities o Skill/Knowledge | C - Communication T - Training PS - Performance Support (i.e. job aids; on-line help) JD - Job Design / Org Design (i.e. new position or add'l roles) O - Other
[7 empty] | C | T | PS | JD | O
[5 empty] | H | Skill/Knowledge | C |  |  |  |  | All Piedmont Employees / HRBPs / Heads up to managers | **Heads up communication Sept. 5 that the rewards program will end in Nov.
1 |  |  | Michael C Fina (MC Fina), Piedmont's service and retirement award provider | OC Tanner, Duke Energy's service and retirement award provider | L | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs / Manager heads up | Bundled communication ('read package') - new vendor and process / HRBP Training
1a |  |  | Michael C Fina (MC Fina), Piedmont's service and retirement award provider | OC Tanner, Duke Energy's service and retirement award provider | L | Skill/Knowledge |  |  |  |  | O |  | Engaging in pricing impact discussions with OC Tanner; is there an impact by bringing in Piedmont employees into Duke's plan? - TBD
2 |  |  | Piedmont recognition awards - 1 year and 3 year | Duke Energy - 5 years only | H | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs / Manager heads up | 1 and 3 year awards (Piedmont's previous plan) will not be implemented into Duke Energy's program / Service Award plaque and gift every 5 years and retirement plaque and gift
3 |  |  | Separate Rewards and Recognition Program | Business case for linking Rewards and Recognition and Service and Retirement platform into a common contract | H | Skill/Knowledge | C | T |  |  |  | All Piedmont Employees / HRBPs | Need a solution for 'Stranded Points' (employees get taxed on the points received, but may not have enough points to redeem for a gift) | As of 3/31/17 - 89 employees below 400 points
3a |  |  | Stranded Points' | No program | H | Skill/Knowledge | C | T |  |  |  | Piedmont Managers | Nov. 30 end date for Piedmont Rewards and Recognition program; need to communicate to managers regarding 'stranded point' process prior to this deadline
|  |  |  | Service and Retirement Awards Program | L |  | C | T |  |  |  | All Piedmont Employees | Bundled communication to Piedmont Employees / HRBP Training
4 |  |  | Can currently select points instead of service award gift | The option of choosing points in lieu of a service award gift will be eliminated after Nov. 1, 2017. | H |  | C |  |  |  |  | All Piedmont Employees | **Included in - Heads up communication Sept. 5 that the rewards program will end in Nov.
|  |  | Full-time/part-time employees - upon completion of 5 yrs. of continuous service and end of every 5 years of continuous service thereafter. Manager presents awards. HR responsible for identifying employees to be honored and for distributing materials to management for award presentation. | Service Awards Eligibility -Full-time/part-time employees - every 5 years of service (at 5 years of service and continuing up to 50 years of service) /determined using the employee’s service date. Expires after two years of the previous milestone date. Employees, who retire within one year of the time they would be eligible for a service award, will receive the Service Award Program Brochure to choose a service award gift for the anniversary year they are celebrating. For example, an employee who retires with 24 years and two months of service will receive his/her choice of the 25-year awards. | L |  | C |  |  |  |  | All Piedmont Employees
Ordering a Gift – Service Awards - Employees receive a Lucite framed certificate and will be able to order a gift online, as described below.
Certificate presented to employee by immediate supervisor at an informal gathering on or as near as possible to the employee’s anniversary date. Supervisors will receive an e-mail notification that includes a link to recognition training from OC Tanner. The notification will be sent to the supervisor the day after the employee places an award selection. Supervisors are strongly encouraged to review this on-line training.
Ordering a Gift – Retirement Awards - Eligible retirees (age 50 with 20 years of service) will receive a letter at their home address on record with instructions for accessing the online site or placing their order by phone. Reminder notices are sent. Gift shipped to the retiree's home. Employees can contact the myHR Service Center at 888-465-1300 and select the option for a representative to ask questions concerning the retirement award order.
The retirement award should serve as the employee’s retirement recognition from the Company. Additional gifts from the Company are not appropriate.  Management may wish to recognize the employee based on the employee’s position, job responsibilities and organizational interfaces. An informal gathering may be a staff meeting, special short meeting, team meeting or another activity. Minimal expenditures for informal recognition events may be funded by the department. While there is no longer a specific dollar guideline, departments should continue to manage retiree events in a cost conscious manner in the range of $500-$1,000.  Employees attending retirement activities for others are not reimbursed for travel expenses. Supervisors should manage employee attendance according to business needs. If the event is held during normal work hours, this should be coded as excused time with pay.